## Sheet1
Project Plan | [12 empty] | @
Project Name:- STACAMATICS Phase 1 Name- Basic SaaS Offering with AGI Location- Chennai , TN, India | [5 empty] | Project Start Date:-July 2024 Project End Date- June 2027 Total Duration- 36 Months Phase 1 Start Date- July 2024 Phase 1 End Date- Dec 2024 Phase 1 Duration - 6 Months
Sl | Task | Milestone | Status | Planned Start Date /Time | Planned End Date/Time | Duration | Owner | Remarks | Actual Start Date/Time | Actual Start Date/Time | Actual Duration | Additional Comments
P1 | Initiation
P1.1 | Prepare Project Charter |  |  | 2024-07-01 09:00 | 2024-07-01 17:00 | 8:00
P1.2 | Initial Team Setup |  |  | 2024-07-02 09:00 | 2024-07-12
P1.3 | Prepare JD |  | Complete | 2024-07-03 09:00 | 2024-07-15
P1.4 | Short list Candidates for dev, DevOps, Front end, DB |  | In Progress
P1.5 | Prepare for conducting interview and selection Process |  | In Progress
P1.6 | Conduct Interviews/Tests
P1.7 | Milestone -Team On Boarding Completed
P1.8 | Milestone-Team setup & Structure/Roles defined
P1.9 | Milestone-Stateholder Register Prepared
P1.10 | Plan for Project Kick-off and send Invite
P1.11 | Milestone-Project Kick-off completed |  |  | 2024-09-18 09:00 | 2024-09-18 10:00 | 1:00
P2 | Planning
P2.1 | Requirement gathering
P2.11 | Phase 1 Detail Requirement Spec |  |  | 2024-09-18
P2.12 | Phase 1 Review Functional Requirement
P2.13 | MIlestone-Phase 1 Functional Requirement & SRS Finalized |  |  | 2024-09-23
P2.14 | Phase 1 Review Functional Requirement
P2.2 | Project Documentaion
P2.21 | Prepeare BRS |  | In Progress
P2.22 | Review BRS
P2.23 | Approve & Finalise BRS
P2.24 | Prepeare SRS |  | In Progress
P2.25 | Review SRS
P2.26 | Approve & Finalise SRS
P2.27 | Prepeare PS |  | In Progress
P2.28 | Review PS
P2.29 | Approve & Finalise PS
P2.30 | Clearly Define Scope & Budget
P2.31 | Capture Milestones
P2.32 | Communication Plan
P2.33 | Prepare Project Plan- Overall
P2.34 | Review Plan with Stateholders
P2.35 | Prepare Phase 1 Project Plan- Overall |  | In Progress | 2024-09-18 09:00 | 2024-09-20 17:00
P2.36 | Review Phase 1 Plan |  |  | 2024-09-23 11:00 | 2024-09-23 16:00 | 5:00
P2.37 | Baseline the phase 1 Plan |  |  | 2024-09-23 16:00 | 2024-09-23 16:00
P2.38 | Prepare User Manual
P2.39 | Review User Manual
P2.40 | Finalise User Manual
P2.3 | System Design & Architecture
P2.31 | MVP - 1 Trip Flow |  | In Progress | 2024-09-16 | 2024-09-25
P2.32 | ERD for Phase 1
P2.33 | DB Design
P2.34 | UI/UX Design
P2.35 | Design pages for CONCOR Demo |  | In Progress | 2024-09-30 15:00 | 2024-10-01 17:00 | 12:00 | Safie
Ui/UX for Web Design
Ui/UX for Mobile devices
Review the Pages
Finalize the pages
P2.36 | Interface Design
P2.37 | Reporting Dashboard Design
P2.38 | EDI Design
P2.39 | Architectural Diagram
P2.40 | Data Flow design
P2.41 | Milestone- Finalise architectural & Design doc
P2.42 | List of IOT devices to be used
P2.43 | LIst of Interface to connect to IOTs
P2.44 | Test plan for connectivity checks
P2.45 | Test plan for Overall Developed modules
P3 | Execution
P3.1 | Setup Dev Environment
P3.11 | Vscode
P3.12 | Github
P3.13 | AWS
P3.14 | Milestone- Intial Setup completed for Development Env
P3.2 | Development
P3.2.1 | Flow wise Module segregation
P3.2.2 | Module 1 assigned
P3.2.3 | Moodule 2 assigned
P3.2.4 | Module 3 assigned
P3.2.5 | Intergration of the modules for functional test
P3.2.6 | MIlestone-Ist Integration of Module 1, 2, 3 Successful
P3.3 | Daily Status Team Meeting
P3.4 | Progress Tracking
P3.5 | Report Progress
P3.6 | Budget & Schedule Checks
P4 | Monitoring & Control
P4.1 | Track Budget Vs Time
P4.2 | Track Project Goals
P4.3 | Quality Control
P4.4 | Team Performance
P4.5 | Risk Management
P4.6 | Test execution
P5 | Closure
P5.1 | Retrospective Meeting
P5.2 | Lesson Learnt
P5.3 | Project Closure Report
P6 | Implementation
P6.1 | Demo version Tested
P6.2 | Env Setup at client site
P6.3 | Demo version installated
P6.4 | Demo at client location
P6.5 | Issue Resolution
P6.6 | Milestone-Demo Successfully completed
P6.7 | Actual Implemetaion at Client site
P6.8 | User Training
P6.9 | Support , if issues
In Progress
Completed
Pending
Formulas:
Planned End Date/Time = [Planned Start Date /Time]+[Duration]
Planned End Date/Time = [Planned Start Date /Time]
Planned Start Date /Time = [Planned End Date/Time, row above]

## Stack_Flow
Phase 1- StackFlow
Tasks | Estimated Start Date | Estimated End date | Owner | Remarks
Step 1- Container Trailer Arrival at Entry point of the Entry Gate of the Yard.
Step 2- Entry Gate Inspection officer ( GIO) checks if pre-booked, if yes , go to Step3
Step3- GIO checks SMS or Print out, verify with System operator at entry gate location
Step4- System Operator verifies and confirms “Accept” in the system.
Step5- On “Accept” clicking 1. automated SMS would be sent to the Sender, trailer’s driver confirming the container arrived and accepted in the yard( may be billing for the container estimated time of parking ( ETP) starts from that moment) 2. Current status of the booking would be available on the app or website Nearest RST would be located 3. Job would be assigned & Posted to the RST operator 4. Available parking bay would be assigned and flashed in the system 5. System would identify the correct Yard location for the container to be stacked based on pre-booked information 6. ExitGate system operator (?) or GIO would receive the notification about the acceptance details additionally estimated exit time of the trailer.
Step6- System operator would handover physical paper Map to the GIO for trailer driver to locate and follow direction to the allotted parking bay area along with a paper or digital(?)tagging token with entry timestamp and estimated exit time
The Gate Security will open the entry gate and allow the trailer to move forward to the parking area.
Step7- Post Step12- Trailer moves to ExitGate. ExitGate GIO collects paper Map & paper tagging token and allow trailer to exit
Step8- System operator confirms Container Stacked & StackFlow completed. SMS sent to sender.
Step 9- RST will “Accept “ the assigned job , System shows container details with from which parking bay and to which yard location.
Step 10- RST reach the parking bay area to pick up the container
Step 11- RST operator clicks pic before picking up the container from trailer(?)
Step12- RST picks up the container
Step13- RST moves with container and stacks it to the assigned slot
Step14- Once all containers are picked from trailer , RST confirms Trailers free
Step15- Once all containers are stacked , RST clicks pic & confirms “Job Done”
Step16-System makes RST free and show available for the next job

## Sheet4
MIlestone List for Phase 1 Delivery
Task | Date | Revised Milestone Date | Responsible | Remarks
Start of Phase 1 Activity | 2024-09-30
REadiness of UI/UX for Demo Pages for Concor | 2024-10-01
Functional Flow Finalize for phase 1 | 2024-10-04 |  |  | 10/10- It is still in progress, few changes in Gate Management Module incorporated
Pahse 1 UI/UX pages details & Duration |  |  | Shafi | 10/10- Shafi to confirm the pages designed till date and review with functional requirement
Phase 1 UI/UX pages review |  |  | Krishna, Molly, Swetha, Abhiraj
Architectural design for Phase 1 |  |  | Krishna
Tasklist collection for Pahse 1 Delivery |  |  | Molly
List of SW app /platform required |  |  | Krishna
Buy LIcense/download free ver
Set Dev Environment
Start Coding for Phase 1
Complete Coding for Phase 1
Completion of UI/UX pages for web & Mobile |  |  | Shafi
UI/UX and Code integration |  |  | DevOps
Test Integrated System |  |  | Tester
Review & rework on findings
Retest & finalise the delivery
Run in-house Demo | 2024-11-15
All known issues/Errors addressed | 2024-11-25
Deliver Phase 1 | 2024-11-29
Implement Phase 1
Support Phase 1 Implementaion
Data Collection from Phase 1

## UIUX
UI/UX Pages
Sl No | Main Module | Sub Module | Purpose | Page Name | Total number of Pages for Web | Total number of Pages for Mobile | Start Date | End Date | Review Date/Reviewer | Remarks
1 | 2. GMM | 2.1 Vendor Booking Module | Register
Prior Booking
Booking Confirmation ID
Booking Acceptance